## Resource_Table
ID | Indicators | Resource name | Type | Material label | Initials | Group | Max.Units | Std.Rate | Ovt.Rate | Cost/Use | Accrue At | Base Calendar | Code
1 |  | Management | Work |  | M |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
2 |  | Product Engineering | Work |  | P |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
3 |  | Project Manager | Work |  | P |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
4 |  | Marketing | Work |  | M |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
5 |  | Process Engineer | Work |  | P |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
6 |  | Manufacturing Engineer | Work |  | M |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
7 |  | Safety | Work |  | S |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
8 |  | Legal | Work |  | L |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
9 |  | Accounting | Work |  | A |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
10 |  | Customer | Work |  | C |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
11 |  | Purchasing | Work |  | P |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard

## Assignment_Table
ID | Task name | Resource name | Work | Duration
1 | New product opportunity identified | Management | 0 hrs | 0 wks
2 | New product opportunity identified | Product Engineering | 0 hrs | 0 wks
3 | Describe new product idea (1-page written disclosure) | Product Engineering | 16 hrs | 0.4 wks
4 | Gather information required for go/no-go decision | Product Engineering | 48 hrs | 1.2 wks
5 | Convene opportunity of screening committee (decision to pursue idea or not) | Product Engineering | 8 hrs | 0.2 wks
6 | Decision point - go/no-go to preliminary investigation | Management | 0 hrs | 0 wks
7 | Decision point - go/no-go to preliminary investigation | Product Engineering | 0 hrs | 0 wks
8 | Assign resources to preliminary investigation | Management | 8 hrs | 0.2 wks
9 | Develop preliminary investigation plan | Product Engineering | 40 hrs | 1 wk
10 | Develop preliminary investigation plan | Project Manager | 40 hrs | 1 wk
11 | Evaluate the market | Marketing | 80 hrs | 2 wks
12 | Analyze the competition | Marketing | 40 hrs | 1 wk
13 | Produce lab scale product | Product Engineering | 80 hrs | 2 wks
14 | Evaluate internal product | Product Engineering | 40 hrs | 1 wk
15 | Identify production process steps required for manufacture | Process Engineer | 40 hrs | 1 wk
16 | Assess manufacturing capabilities | Product Engineering | 80 hrs | 2 wks
17 | Assess manufacturing capabilities | Manufacturing Engineer | 80 hrs | 2 wks
18 | Determine safety issues | Safety | 80 hrs | 2 wks
19 | Determine environmental issues | Product Engineering | 80 hrs | 2 wks
20 | Determine environmental issues | Legal | 80 hrs | 2 wks
21 | Review legal issues | Legal | 80 hrs | 2 wks
22 | Review legal issues | Project Manager | 80 hrs | 2 wks
23 | Perform financial evaluation | Accounting | 80 hrs | 2 wks
24 | Develop risk analysis | Product Engineering | 40 hrs | 1 wk
25 | Develop risk analysis | Project Manager | 40 hrs | 1 wk
26 | Draft initial development stage plan | Product Engineering | 80 hrs | 2 wks
27 | Conduct preliminary stage review decision | Management | 16 hrs | 0.4 wks
28 | Conduct preliminary stage review decision | Product Engineering | 16 hrs | 0.4 wks
29 | Conduct preliminary stage review decision | Project Manager | 16 hrs | 0.4 wks
30 | Decision point - go/no-go to development stage | Management | 0 hrs | 0 wks
31 | Decision point - go/no-go to development stage | Project Manager | 0 hrs | 0 wks
32 | Assign resources to development stage plan | Management | 8 hrs | 0.2 wks
33 | Assign resources to development stage plan | Project Manager | 8 hrs | 0.2 wks
34 | Gather market information | Product Engineering | 120 hrs | 3 wks
35 | Gather market information | Marketing | 120 hrs | 3 wks
36 | Identify and contact customer sample group | Marketing | 40 hrs | 1 wk
37 | Perform competitor analysis | Marketing | 120 hrs | 3 wks
38 | Redefine product requirements | Product Engineering | 80 hrs | 2 wks
39 | Establish product characteristics (performance criteria) | Product Engineering | 16 hrs | 0.4 wks
40 | Develop prototype process | Product Engineering | 80 hrs | 2 wks
41 | Produce prototype product | Product Engineering | 200 hrs | 5 wks
42 | Conduct internal product review | Management | 40 hrs | 1 wk
43 | Conduct internal product review | Product Engineering | 40 hrs | 1 wk
44 | Document patent application process | Product Engineering | 80 hrs | 2 wks
45 | Conduct marketing/technical review | Marketing | 736 hrs | 18.4 wks
46 | Conduct marketing/technical review | Product Engineering | 736 hrs | 18.4 wks
47 | Redesign process (if necessary) | Product Engineering | 80 hrs | 2 wks
48 | Redesign process (if necessary) | Process Engineer | 80 hrs | 2 wks
49 | Modify prototype process | Process Engineer | 120 hrs | 3 wks
50 | Develop plan for customer product testing | Project Manager | 40 hrs | 1 wk
51 | Produce product for customer evaluation | Product Engineering | 200 hrs | 5 wks
52 | Produce product for customer evaluation | Marketing | 200 hrs | 5 wks
53 | Produce product for customer evaluation | Project Manager | 200 hrs | 5 wks
54 | Conduct preliminary manufacturing process review | Process Engineer | 80 hrs | 2 wks
55 | Conduct preliminary manufacturing process review | Manufacturing Engineer | 80 hrs | 2 wks
56 | Conduct customer evaluations of prototype product | Product Engineering | 160 hrs | 4 wks
57 | Conduct customer evaluations of prototype product | Project Manager | 160 hrs | 4 wks
58 | Conduct customer evaluations of prototype product | Customer | 160 hrs | 4 wks
59 | Conduct marketing/technical review | Management | 16 hrs | 0.4 wks
60 | Conduct marketing/technical review | Product Engineering | 16 hrs | 0.4 wks
61 | Conduct marketing/technical review | Marketing | 16 hrs | 0.4 wks
62 | Prepare preliminary manufacturing design | Product Engineering | 160 hrs | 4 wks
63 | Evaluate contract manufacturing option | Legal | 80 hrs | 2 wks
64 | Evaluate contract manufacturing option | Process Engineer | 80 hrs | 2 wks
65 | Review legal and patent considerations | Management | 80 hrs | 2 wks
66 | Review legal and patent considerations | Legal | 80 hrs | 2 wks
67 | Perform environmental review | Product Engineering | 80 hrs | 2 wks
68 | Conduct product safety review | Product Engineering | 120 hrs | 3 wks
69 | Conduct product safety review | Safety | 120 hrs | 3 wks
70 | Perform evaluate/predict product cycle time | Product Engineering | 120 hrs | 3 wks
71 | Perform evaluate/predict product cycle time | Project Manager | 120 hrs | 3 wks
72 | Update financial analysis | Accounting | 80 hrs | 2 wks
73 | Risk analysis | Product Engineering | 80 hrs | 2 wks
74 | Review preliminary investigation criteria | Management | 16 hrs | 0.4 wks
75 | Review preliminary investigation criteria | Product Engineering | 16 hrs | 0.4 wks
76 | Review preliminary investigation criteria | Legal | 16 hrs | 0.4 wks
77 | Develop pilot stage plan | Product Engineering | 40 hrs | 1 wk
78 | Develop pilot stage plan | Project Manager | 40 hrs | 1 wk
79 | Conduct development stage review | Product Engineering | 16 hrs | 0.4 wks
80 | Conduct development stage review | Project Manager | 16 hrs | 0.4 wks
81 | Conduct development stage review | Process Engineer | 16 hrs | 0.4 wks
82 | Decision point - go/no-go to pilot stage | Management | 0 hrs | 0 wks
83 | Decision point - go/no-go to pilot stage | Project Manager | 0 hrs | 0 wks
84 | Assign pilot stage resources | Management | 8 hrs | 0.2 wks
85 | Assign pilot stage resources | Project Manager | 8 hrs | 0.2 wks
86 | Secure customer commitment to participate in commercialization trials | Legal | 40 hrs | 1 wk
87 | Secure customer commitment to participate in commercialization trials | Project Manager | 40 hrs | 1 wk
88 | Schedule/reserve pilot production facility | Project Manager | 40 hrs | 1 wk
89 | Resolve raw material and finish products logistics | Product Engineering | 40 hrs | 1 wk
90 | Resolve raw material and finish products logistics | Project Manager | 40 hrs | 1 wk
91 | Review trial plan and requirements | Product Engineering | 40 hrs | 1 wk
92 | Review trial plan and requirements | Project Manager | 40 hrs | 1 wk
93 | Start trial material production | Product Engineering | 240 hrs | 6 wks
94 | Monitor customer trials | Product Engineering | 160 hrs | 4 wks
95 | Review preliminary trial results | Product Engineering | 80 hrs | 2 wks
96 | Review preliminary trial results | Project Manager | 80 hrs | 2 wks
97 | Continue trial material production | Product Engineering | 240 hrs | 6 wks
98 | Complete customer trial monitoring | Product Engineering | 160 hrs | 4 wks
99 | Confirm sales and marketing strategies | Marketing | 40 hrs | 1 wk
100 | Confirm sales and marketing strategies | Project Manager | 40 hrs | 1 wk
101 | Confirm product safety | Project Manager | 40 hrs | 1 wk
102 | Confirm product safety | Safety | 40 hrs | 1 wk
103 | Reevaluate manufacturing processes | Process Engineer | 120 hrs | 3 wks
104 | Develop commercialization plan | Product Engineering | 120 hrs | 3 wks
105 | Develop commercialization plan | Marketing | 120 hrs | 3 wks
106 | Review financials | Accounting | 40 hrs | 1 wk
107 | Review patent and legal issues | Legal | 80 hrs | 2 wks
108 | Assign commercialization leadership responsibility and resources | Management | 16 hrs | 0.4 wks
109 | Assign commercialization leadership responsibility and resources | Project Manager | 16 hrs | 0.4 wks
110 | Pilot stage review and commercialization decision | Management | 16 hrs | 0.4 wks
111 | Pilot stage review and commercialization decision | Product Engineering | 16 hrs | 0.4 wks
112 | Pilot stage review and commercialization decision | Marketing | 16 hrs | 0.4 wks
113 | Pilot stage review and commercialization decision | Process Engineer | 16 hrs | 0.4 wks
114 | Confirm product specification | Product Engineering | 24 hrs | 0.6 wks
115 | Confirm product specification | Manufacturing Engineer | 24 hrs | 0.6 wks
116 | Confirm customer specification acceptance and trial participation | Product Engineering | 80 hrs | 2 wks
117 | Confirm customer specification acceptance and trial participation | Project Manager | 80 hrs | 2 wks
118 | Develop manufacturing process requirements | Process Engineer | 80 hrs | 2 wks
119 | Develop manufacturing process requirements | Manufacturing Engineer | 80 hrs | 2 wks
120 | Design and order new equipment | Product Engineering | 240 hrs | 6 wks
121 | Design and order new equipment | Purchasing | 240 hrs | 6 wks
122 | Install and test new equipment or equipment modifications | Product Engineering | 240 hrs | 6 wks
123 | Install and test new equipment or equipment modifications | Manufacturing Engineer | 240 hrs | 6 wks
124 | Confirm manufacturing capabilities | Manufacturing Engineer | 80 hrs | 2 wks
125 | Develop and review production trial plan (resolve logistics issues) | Product Engineering | 40 hrs | 1 wk
126 | Develop and review production trial plan (resolve logistics issues) | Project Manager | 40 hrs | 1 wk
127 | Start production of commercial product quantities | Product Engineering | 320 hrs | 8 wks
128 | Start production of commercial product quantities | Manufacturing Engineer | 320 hrs | 8 wks
129 | Monitor customer acceptance testing | Product Engineering | 240 hrs | 6 wks
130 | Monitor customer acceptance testing | Project Manager | 240 hrs | 6 wks
131 | Perform internal product testing | Product Engineering | 120 hrs | 3 wks
132 | Review production performance results | Management | 80 hrs | 2 wks
133 | Review production performance results | Product Engineering | 80 hrs | 2 wks
134 | Review production performance results | Project Manager | 80 hrs | 2 wks
135 | Identify long term production requirements | Process Engineer | 120 hrs | 3 wks
136 | Identify long term production requirements | Manufacturing Engineer | 120 hrs | 3 wks
137 | Recalculate product economics | Product Engineering | 80 hrs | 2 wks
138 | Recalculate product economics | Marketing | 80 hrs | 2 wks
139 | Recalculate product economics | Accounting | 80 hrs | 2 wks
140 | Affirm decision to continue commercialization program | Management | 16 hrs | 0.4 wks
141 | Affirm decision to continue commercialization program | Project Manager | 16 hrs | 0.4 wks
142 | Determine if product is meeting customer cost/performance expectations | Management | 480 hrs | 12 wks
143 | Determine if product is meeting customer cost/performance expectations | Project Manager | 480 hrs | 12 wks
144 | Determine if sales have met projections | Management | 480 hrs | 12 wks
145 | Determine if sales have met projections | Marketing | 480 hrs | 12 wks
146 | Determine if product is sustaining its position against competitive response | Management | 240 hrs | 6 wks
147 | Determine if product is sustaining its position against competitive response | Marketing | 240 hrs | 6 wks
148 | Evaluate manufacturing process for stability and cost effectiveness | Project Manager | 320 hrs | 8 wks
149 | Evaluate manufacturing process for stability and cost effectiveness | Manufacturing Engineer | 320 hrs | 8 wks
150 | Determine if current economics are consistent with projected economics | Marketing | 120 hrs | 3 wks
151 | Evaluate opportunities to expand product or product line | Management | 120 hrs | 3 wks
152 | Evaluate opportunities to expand product or product line | Product Engineering | 120 hrs | 3 wks
153 | Evaluate opportunities to expand product or product line | Marketing | 120 hrs | 3 wks