## Resource_Table
ID | Indicators | Resource name | Type | Material label | Initials | Group | Max.Units | Std.Rate | Ovt.Rate | Cost/Use | Accrue At | Base Calendar | Code
1 |  | Project Director | Work |  | P |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
2 |  | Project Manager | Work |  | P |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
3 |  | Acceptor | Work |  | A |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
4 |  | Application Architect | Work |  | A |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
5 |  | Technical Architect | Work |  | T |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
6 |  | Quality Assurance Manager | Work |  | Q |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
7 |  | Contracts Manager | Work |  | C |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard

## Assignment_Table
ID | Task name | Resource name | Work | Duration
1 | Identify Goals and Objectives | Project Director | 8 hrs | 1 day?
2 | Develop Strategies and Plans | Project Director | 8 hrs | 1 day?
3 | Research Previous Experience | Project Manager | 8 hrs | 1 day?
4 | Develop Project Charter | Project Manager | 4 hrs | 0.5 days?
5 | Develop Project Charter | Acceptor | 4 hrs | 0.5 days?
6 | Conduct Planning Workshop | Project Director | 8 hrs | 1 day?
7 | Document Project Costs and Benefits | Application Architect | 4 hrs | 0.5 days?
8 | Document Project Costs and Benefits | Technical Architect | 4 hrs | 0.5 days?
9 | Document Project Costs and Benefits | Project Manager | 4 hrs | 0.5 days?
10 | Develop High Level Work Breakdown Structure | Project Manager | 8 hrs | 1 day?
11 | Conduct Peer Review | Project Manager | 8 hrs | 1 day?
12 | Prepare Preliminary Project Scope Statement | Project Manager | 4 hrs | 0.5 days?
13 | Prepare Preliminary Project Scope Statement | Acceptor | 4 hrs | 0.5 days?
14 | Prepare Facilities | Project Manager | 8 hrs | 1 day?
15 | Set Up Project Standards and Procedures | Quality Assurance Manager | 8 hrs | 1 day?
16 | Set Up Project Management Tools | Project Manager | 8 hrs | 1 day?
17 | Set Up Project Book | Project Manager | 8 hrs | 1 day?
18 | Document Scope Management Plan | Project Manager | 8 hrs | 1 day?
19 | Specify Deliverables and Acceptance Criteria | Project Manager | 8 hrs | 1 day?
20 | Define Scope | Project Manager | 8 hrs | 1 day?
21 | Document Assumptions | Project Manager | 8 hrs | 1 day?
22 | Build Work Breakdown Structure | Project Manager | 8 hrs | 1 day?
23 | Develop Resource Plans | Project Manager | 8 hrs | 1 day?
24 | Prepare Project Estimates | Project Manager | 8 hrs | 1 day?
25 | Define Dependencies and Develop Project Schedule | Project Manager | 8 hrs | 1 day?
26 | Document Assumptions | Project Manager | 8 hrs | 1 day?
27 | Document Risk Management Plan | Project Manager | 4 hrs | 0.5 days?
28 | Document Risk Management Plan | Acceptor | 4 hrs | 0.5 days?
29 | Identify Risks | Project Manager | 8 hrs | 1 day?
30 | Analyze Risks | Project Manager | 8 hrs | 1 day?
31 | Document Risk Management Plans | Project Manager | 4 hrs | 0.5 days?
32 | Document Risk Management Plans | Acceptor | 4 hrs | 0.5 days?
33 | Document Quality Management Plan | Quality Assurance Manager | 4 hrs | 0.5 days?
34 | Document Quality Management Plan | Acceptor | 4 hrs | 0.5 days?
35 | Develop Organization Structure | Project Director | 8 hrs | 1 day?
36 | Develop Staffing Plan | Project Director | 8 hrs | 1 day?
37 | Determine Procurement Requirements | Contracts Manager | 8 hrs | 1 day?
38 | Define Subcontractor Scope | Contracts Manager | 8 hrs | 1 day?
39 | Identify Potential Subcontractors | Contracts Manager | 8 hrs | 1 day?
40 | Identify Subcontract Type | Contracts Manager | 8 hrs | 1 day?
41 | Document Subcontractor Management Plan | Contracts Manager | 4 hrs | 0.5 days?
42 | Document Subcontractor Management Plan | Acceptor | 4 hrs | 0.5 days?
43 | Prepare Financial Plan | Project Manager | 8 hrs | 1 day?
44 | Document Assumptions | Project Manager | 8 hrs | 1 day?
45 | Document Communications Management Plan | Project Manager | 4 hrs | 0.5 days?
46 | Document Communications Management Plan | Acceptor | 4 hrs | 0.5 days?
47 | Document Configuration Management Plan | Project Manager | 4 hrs | 0.5 days?
48 | Document Configuration Management Plan | Acceptor | 4 hrs | 0.5 days?
49 | Document Data Management Plan | Project Manager | 4 hrs | 0.5 days?
50 | Document Data Management Plan | Acceptor | 4 hrs | 0.5 days?
51 | Document Project Management Plan | Project Manager | 4 hrs | 0.5 days?
52 | Document Project Management Plan | Acceptor | 4 hrs | 0.5 days?
53 | Obtain Resources | Project Director | 8 hrs | 1 day?
54 | Conduct Team Orientation | Project Director | 8 hrs | 1 day?
55 | Assign Responsibilities | Project Manager | 8 hrs | 1 day?
56 | Manage Data Items | Project Manager | 8 hrs | 1 day?
57 | Manage Configuration Items | Project Manager | 8 hrs | 1 day?
58 | Manage Process Data | Project Manager | 8 hrs | 1 day?
59 | Provide General Office Support | Project Manager | 8 hrs | 1 day?
60 | Administer Project Security Processes | Project Manager | 8 hrs | 1 day?
61 | Provide Team Training | Project Manager | 8 hrs | 1 day?
62 | Recognize Success | Project Director | 8 hrs | 1 day?
63 | Participate in Walk-throughs and Reviews | Quality Assurance Manager | 8 hrs | 1 day?
64 | Conduct Inspections and Audits | Quality Assurance Manager | 8 hrs | 1 day?
65 | Conduct Project Reviews | Quality Assurance Manager | 8 hrs | 1 day?
66 | Facilitate Continuous Improvement | Quality Assurance Manager | 8 hrs | 1 day?
67 | Review Progress | Project Director | 8 hrs | 1 day?
68 | Issue Requisition Documents | Contracts Manager | 8 hrs | 1 day?
69 | Evaluate Responses | Contracts Manager | 8 hrs | 1 day?
70 | Negotiate Subcontractor Contract | Contracts Manager | 8 hrs | 1 day?
71 | Authorize Work | Project Manager | 8 hrs | 1 day?
72 | Manage Action Items | Project Manager | 8 hrs | 1 day?
73 | Manage Project Records | Project Manager | 8 hrs | 1 day?
74 | Manage Scope | Project Manager | 8 hrs | 1 day?
75 | Manage Requirements | Project Manager | 8 hrs | 1 day?
76 | Control Decisions | Project Manager | 8 hrs | 1 day?
77 | Control Changes | Project Manager | 8 hrs | 1 day?
78 | Manage Project Acceptance | Project Manager | 4 hrs | 0.5 days?
79 | Manage Project Acceptance | Acceptor | 4 hrs | 0.5 days?
80 | Track Status | Project Manager | 8 hrs | 1 day?
81 | Maintain Project Schedule | Project Manager | 8 hrs | 1 day?
82 | Maintain Work Plans | Project Manager | 8 hrs | 1 day?
83 | Monitor Cost/Schedule Variance | Project Manager | 8 hrs | 1 day?
84 | Control Costs | Project Director | 8 hrs | 1 day?
85 | Maintain Financial Plan | Project Director | 8 hrs | 1 day?
86 | Control Quality | Quality Assurance Manager | 8 hrs | 1 day?
87 | Participate in Testing | Quality Assurance Manager | 8 hrs | 1 day?
88 | Measure Quality Levels | Quality Assurance Manager | 8 hrs | 1 day?
89 | Manage Communications | Project Manager | 8 hrs | 1 day?
90 | Meet With Team | Project Manager | 8 hrs | 1 day?
91 | Monitor Team Morale | Project Manager | 8 hrs | 1 day?
92 | Conduct Team Performance Reviews | Project Manager | 8 hrs | 1 day?
93 | Report Weekly Status | Project Manager | 4 hrs | 0.5 days?
94 | Report Weekly Status | Acceptor | 4 hrs | 0.5 days?
95 | Report Monthly Status | Project Manager | 4 hrs | 0.5 days?
96 | Report Monthly Status | Acceptor | 4 hrs | 0.5 days?
97 | Monitor Satisfaction | Project Director | 8 hrs | 1 day?
98 | Resolve Issues | Project Director | 8 hrs | 1 day?
99 | Manage Risks | Project Manager | 8 hrs | 1 day?
100 | Manage Subcontractor Contract | Contracts Manager | 8 hrs | 1 day?
101 | Assess Satisfaction | Project Manager | 8 hrs | 1 day?
102 | Summarize Project Results and Lessons Learned | Project Manager | 8 hrs | 1 day?
103 | Review and Recognize Team Performance | Project Manager | 8 hrs | 1 day?
104 | Close Out the Project Records | Project Manager | 8 hrs | 1 day?
105 | Review and Reconcile Financial Performance | Project Manager | 8 hrs | 1 day?
106 | Close Contract | Contracts Manager | 8 hrs | 1 day?