## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Software Development Plan | 95.75 days | Mon 8/03/20 | Mon 12/14/20 |  | 0
1 | Yes | Auto Scheduled | Scope | 3.5 days | Mon 8/03/20 | Thu 8/06/20 |  | 1
2 | Yes | Auto Scheduled | Determine project scope | 4 hrs | Mon 8/03/20 | Mon 8/03/20 |  | 2
3 | Yes | Auto Scheduled | Secure project sponsorship | 1 day | Mon 8/03/20 | Tue 8/04/20 | 2 | 2
4 | Yes | Auto Scheduled | Define preliminary resources | 1 day | Tue 8/04/20 | Wed 8/05/20 | 3 | 2
5 | Yes | Auto Scheduled | Secure core resources | 1 day | Wed 8/05/20 | Thu 8/06/20 | 4 | 2
6 | Yes | Auto Scheduled | Scope complete | 0 days | Thu 8/06/20 | Thu 8/06/20 | 5 | 2
7 | Yes | Auto Scheduled | Analysis/Software Requirements | 14 days | Thu 8/06/20 | Wed 8/26/20 |  | 1
8 | Yes | Auto Scheduled | Conduct needs analysis | 5 days | Thu 8/06/20 | Thu 8/13/20 | 6 | 2
9 | Yes | Auto Scheduled | Draft preliminary software specifications | 3 days | Thu 8/13/20 | Tue 8/18/20 | 8 | 2
10 | Yes | Auto Scheduled | Develop preliminary budget | 2 days | Tue 8/18/20 | Thu 8/20/20 | 9 | 2
11 | Yes | Auto Scheduled | Review software specifications/budget with team | 4 hrs | Thu 8/20/20 | Thu 8/20/20 | 10 | 2
12 | Yes | Auto Scheduled | Incorporate feedback on software specifications | 1 day | Fri 8/21/20 | Fri 8/21/20 | 11 | 2
13 | Yes | Auto Scheduled | Develop delivery timeline | 1 day | Mon 8/24/20 | Mon 8/24/20 | 12 | 2
14 | Yes | Auto Scheduled | Obtain approvals to proceed (concept, timeline, budget) | 4 hrs | Tue 8/25/20 | Tue 8/25/20 | 13 | 2
15 | Yes | Auto Scheduled | Secure required resources | 1 day | Tue 8/25/20 | Wed 8/26/20 | 14 | 2
16 | Yes | Auto Scheduled | Analysis complete | 0 days | Wed 8/26/20 | Wed 8/26/20 | 15 | 2
17 | Yes | Auto Scheduled | Design | 14.5 days | Wed 8/26/20 | Tue 9/15/20 |  | 1
18 | Yes | Auto Scheduled | Review preliminary software specifications | 2 days | Wed 8/26/20 | Fri 8/28/20 | 16 | 2
19 | Yes | Auto Scheduled | Develop functional specifications | 5 days | Fri 8/28/20 | Fri 9/04/20 | 18 | 2
20 | Yes | Auto Scheduled | Develop prototype based on functional specifications | 4 days | Fri 9/04/20 | Thu 9/10/20 | 19 | 2
21 | Yes | Auto Scheduled | Review functional specifications | 2 days | Thu 9/10/20 | Mon 9/14/20 | 20 | 2
22 | Yes | Auto Scheduled | Incorporate feedback into functional specifications | 1 day | Mon 9/14/20 | Tue 9/15/20 | 21 | 2
23 | Yes | Auto Scheduled | Obtain approval to proceed | 4 hrs | Tue 9/15/20 | Tue 9/15/20 | 22 | 2
24 | Yes | Auto Scheduled | Design complete | 0 days | Tue 9/15/20 | Tue 9/15/20 | 23 | 2
25 | Yes | Auto Scheduled | Development | 21.75 days | Wed 9/16/20 | Thu 10/15/20 |  | 1
26 | Yes | Auto Scheduled | Review functional specifications | 1 day | Wed 9/16/20 | Wed 9/16/20 | 24 | 2
27 | Yes | Auto Scheduled | Identify modular/tiered design parameters | 1 day | Thu 9/17/20 | Thu 9/17/20 | 26 | 2
28 | Yes | Auto Scheduled | Assign development staff | 1 day | Fri 9/18/20 | Fri 9/18/20 | 27 | 2
29 | Yes | Auto Scheduled | Develop code | 15 days | Mon 9/21/20 | Fri 10/09/20 | 28 | 2
30 | Yes | Auto Scheduled | Developer testing (primary debugging) | 15 days | Thu 9/24/20 | Thu 10/15/20 | 29FS-11.25 days | 2
31 | Yes | Auto Scheduled | Development complete | 0 days | Thu 10/15/20 | Thu 10/15/20 | 30 | 2
32 | Yes | Auto Scheduled | Testing | 48.75 days | Wed 9/16/20 | Mon 11/23/20 |  | 1
33 | Yes | Auto Scheduled | Develop unit test plans using product specifications | 4 days | Wed 9/16/20 | Mon 9/21/20 | 24 | 2
34 | Yes | Auto Scheduled | Develop integration test plans using product specifications | 4 days | Wed 9/16/20 | Mon 9/21/20 | 24 | 2
35 | Yes | Auto Scheduled | Unit Testing | 15 days | Thu 10/15/20 | Thu 11/05/20 |  | 2
36 | Yes | Auto Scheduled | Review modular code | 5 days | Thu 10/15/20 | Thu 10/22/20 | 33;31 | 3
37 | Yes | Auto Scheduled | Test component modules to product specifications | 2 days | Thu 10/22/20 | Mon 10/26/20 | 31;36 | 3
38 | Yes | Auto Scheduled | Identify anomalies to product specifications | 3 days | Mon 10/26/20 | Thu 10/29/20 | 37 | 3
39 | Yes | Auto Scheduled | Modify code | 3 days | Thu 10/29/20 | Tue 11/03/20 | 38 | 3
40 | Yes | Auto Scheduled | Re-test modified code | 2 days | Tue 11/03/20 | Thu 11/05/20 | 39 | 3
41 | Yes | Auto Scheduled | Unit testing complete | 0 days | Thu 11/05/20 | Thu 11/05/20 | 40 | 3
42 | Yes | Auto Scheduled | Integration Testing | 12 days | Thu 11/05/20 | Mon 11/23/20 |  | 2
43 | Yes | Auto Scheduled | Test module integration | 5 days | Thu 11/05/20 | Thu 11/12/20 | 41 | 3
44 | Yes | Auto Scheduled | Identify anomalies to specifications | 2 days | Thu 11/12/20 | Mon 11/16/20 | 43 | 3
45 | Yes | Auto Scheduled | Modify code | 3 days | Mon 11/16/20 | Thu 11/19/20 | 44 | 3
46 | Yes | Auto Scheduled | Re-test modified code | 2 days | Thu 11/19/20 | Mon 11/23/20 | 45 | 3
47 | Yes | Auto Scheduled | Integration testing complete | 0 days | Mon 11/23/20 | Mon 11/23/20 | 46 | 3
48 | Yes | Auto Scheduled | Training | 45.75 days | Wed 9/16/20 | Wed 11/18/20 |  | 1
49 | Yes | Auto Scheduled | Develop training specifications for end users | 3 days | Wed 9/16/20 | Fri 9/18/20 | 24 | 2
50 | Yes | Auto Scheduled | Develop training specifications for helpdesk support staff | 3 days | Wed 9/16/20 | Fri 9/18/20 | 24 | 2
51 | Yes | Auto Scheduled | Identify training delivery methodology (computer based training, classroom, etc.) | 2 days | Wed 9/16/20 | Thu 9/17/20 | 24 | 2
52 | Yes | Auto Scheduled | Develop training materials | 3 wks | Thu 10/15/20 | Thu 11/05/20 | 49;31;50;51 | 2
53 | Yes | Auto Scheduled | Conduct training usability study | 4 days | Thu 11/05/20 | Wed 11/11/20 | 52 | 2
54 | Yes | Auto Scheduled | Finalize training materials | 3 days | Wed 11/11/20 | Mon 11/16/20 | 53 | 2
55 | Yes | Auto Scheduled | Develop training delivery mechanism | 2 days | Mon 11/16/20 | Wed 11/18/20 | 54 | 2
56 | Yes | Auto Scheduled | Training materials complete | 0 days | Wed 11/18/20 | Wed 11/18/20 | 55 | 2
57 | Yes | Auto Scheduled | Documentation | 30.5 days | Wed 9/16/20 | Wed 10/28/20 |  | 1
58 | Yes | Auto Scheduled | Develop Help specification | 1 day | Wed 9/16/20 | Wed 9/16/20 | 24 | 2
59 | Yes | Auto Scheduled | Develop Help system | 3 wks | Wed 9/30/20 | Wed 10/21/20 | 58;29FS-7.5 days | 2
60 | Yes | Auto Scheduled | Review Help documentation | 3 days | Wed 10/21/20 | Mon 10/26/20 | 59 | 2
61 | Yes | Auto Scheduled | Incorporate Help documentation feedback | 2 days | Mon 10/26/20 | Wed 10/28/20 | 60 | 2
62 | Yes | Auto Scheduled | Develop user manuals specifications | 2 days | Wed 9/16/20 | Thu 9/17/20 | 24 | 2
63 | Yes | Auto Scheduled | Develop user manuals | 3 wks | Wed 9/30/20 | Wed 10/21/20 | 62;29FS-7.5 days | 2
64 | Yes | Auto Scheduled | Review all user documentation | 2 days | Wed 10/21/20 | Fri 10/23/20 | 63 | 2
65 | Yes | Auto Scheduled | Incorporate user documentation feedback | 2 days | Fri 10/23/20 | Tue 10/27/20 | 64 | 2
66 | Yes | Auto Scheduled | Documentation complete | 0 days | Wed 10/28/20 | Wed 10/28/20 | 65;61 | 2
67 | Yes | Auto Scheduled | Pilot | 70.25 days | Wed 8/26/20 | Wed 12/02/20 |  | 1
68 | Yes | Auto Scheduled | Identify test group | 1 day | Wed 8/26/20 | Thu 8/27/20 | 16 | 2
69 | Yes | Auto Scheduled | Develop software delivery mechanism | 1 day | Thu 8/27/20 | Fri 8/28/20 | 68 | 2
70 | Yes | Auto Scheduled | Install/deploy software | 1 day | Mon 11/23/20 | Tue 11/24/20 | 47;69;66;56 | 2
71 | Yes | Auto Scheduled | Obtain user feedback | 1 wk | Tue 11/24/20 | Tue 12/01/20 | 70 | 2
72 | Yes | Auto Scheduled | Evaluate testing information | 1 day | Tue 12/01/20 | Wed 12/02/20 | 71 | 2
73 | Yes | Auto Scheduled | Pilot complete | 0 days | Wed 12/02/20 | Wed 12/02/20 | 72 | 2
74 | Yes | Auto Scheduled | Deployment | 5 days | Wed 12/02/20 | Wed 12/09/20 |  | 1
75 | Yes | Auto Scheduled | Determine final deployment strategy | 1 day | Wed 12/02/20 | Thu 12/03/20 | 73 | 2
76 | Yes | Auto Scheduled | Develop deployment methodology | 1 day | Thu 12/03/20 | Fri 12/04/20 | 75 | 2
77 | Yes | Auto Scheduled | Secure deployment resources | 1 day | Fri 12/04/20 | Mon 12/07/20 | 76 | 2
78 | Yes | Auto Scheduled | Train support staff | 1 day | Mon 12/07/20 | Tue 12/08/20 | 77 | 2
79 | Yes | Auto Scheduled | Deploy software | 1 day | Tue 12/08/20 | Wed 12/09/20 | 78 | 2
80 | Yes | Auto Scheduled | Deployment complete | 0 days | Wed 12/09/20 | Wed 12/09/20 | 79 | 2
81 | Yes | Auto Scheduled | Post Implementation Review | 3 days | Wed 12/09/20 | Mon 12/14/20 |  | 1
82 | Yes | Auto Scheduled | Document lessons learned | 1 day | Wed 12/09/20 | Thu 12/10/20 | 80 | 2
83 | Yes | Auto Scheduled | Distribute to team members | 1 day | Thu 12/10/20 | Fri 12/11/20 | 82 | 2
84 | Yes | Auto Scheduled | Create software maintenance team | 1 day | Fri 12/11/20 | Mon 12/14/20 | 83 | 2
85 | Yes | Auto Scheduled | Post implementation review complete | 0 days | Mon 12/14/20 | Mon 12/14/20 | 84 | 2
86 | Yes | Auto Scheduled | Software development template complete | 0 days | Mon 12/14/20 | Mon 12/14/20 | 85 | 1

## Resource_Table
ID | Indicators | Resource name | Type | Material label | Initials | Group | Max.Units | Std.Rate | Ovt.Rate | Cost/Use | Accrue At | Base Calendar | Code
1 |  | Management | Work |  | M |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
2 |  | Project Manager | Work |  | P |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
3 |  | Analyst | Work |  | A |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
4 |  | Developer | Work |  | D |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
5 |  | Testers | Work |  | T |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
6 |  | Trainers | Work |  | T |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
7 |  | Technical Communicators | Work |  | T |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard
8 |  | Deployment Team | Work |  | D |  | 100% | $0.00/hr | $0.00/hr | $0.00 | Prorated | Standard

## Assignment_Table
ID | Task name | Resource name | Work | Duration
14 | Determine project scope | Management | 4 hrs | 4 hrs
15 | Secure project sponsorship | Management | 8 hrs | 1 day
16 | Define preliminary resources | Project Manager | 8 hrs | 1 day
17 | Secure core resources | Project Manager | 8 hrs | 1 day
18 | Conduct needs analysis | Analyst | 40 hrs | 5 days
19 | Draft preliminary software specifications | Analyst | 24 hrs | 3 days
20 | Develop preliminary budget | Project Manager | 16 hrs | 2 days
21 | Review software specifications/budget with team | Project Manager | 4 hrs | 4 hrs
22 | Review software specifications/budget with team | Analyst | 4 hrs | 4 hrs
23 | Incorporate feedback on software specifications | Analyst | 8 hrs | 1 day
24 | Develop delivery timeline | Project Manager | 8 hrs | 1 day
25 | Obtain approvals to proceed (concept, timeline, budget) | Management | 4 hrs | 4 hrs
26 | Obtain approvals to proceed (concept, timeline, budget) | Project Manager | 4 hrs | 4 hrs
27 | Secure required resources | Project Manager | 8 hrs | 1 day
28 | Review preliminary software specifications | Analyst | 16 hrs | 2 days
29 | Develop functional specifications | Analyst | 40 hrs | 5 days
30 | Develop prototype based on functional specifications | Analyst | 32 hrs | 4 days
31 | Review functional specifications | Management | 16 hrs | 2 days
32 | Incorporate feedback into functional specifications | Management | 8 hrs | 1 day
33 | Obtain approval to proceed | Management | 4 hrs | 4 hrs
34 | Obtain approval to proceed | Project Manager | 4 hrs | 4 hrs
35 | Review functional specifications | Developer | 8 hrs | 1 day
36 | Identify modular/tiered design parameters | Developer | 8 hrs | 1 day
37 | Assign development staff | Developer | 8 hrs | 1 day
38 | Develop code | Developer | 120 hrs | 15 days
39 | Developer testing (primary debugging) | Developer | 120 hrs | 15 days
40 | Develop unit test plans using product specifications | Testers | 32 hrs | 4 days
41 | Develop integration test plans using product specifications | Testers | 32 hrs | 4 days
42 | Review modular code | Testers | 40 hrs | 5 days
43 | Test component modules to product specifications | Testers | 16 hrs | 2 days
44 | Identify anomalies to product specifications | Testers | 24 hrs | 3 days
45 | Modify code | Testers | 24 hrs | 3 days
46 | Re-test modified code | Testers | 16 hrs | 2 days
47 | Test module integration | Testers | 40 hrs | 5 days
48 | Identify anomalies to specifications | Testers | 16 hrs | 2 days
49 | Modify code | Testers | 24 hrs | 3 days
50 | Re-test modified code | Testers | 16 hrs | 2 days
51 | Develop training specifications for end users | Trainers | 24 hrs | 3 days
52 | Develop training specifications for helpdesk support staff | Trainers | 24 hrs | 3 days
53 | Identify training delivery methodology (computer based training, classroom, etc.) | Trainers | 16 hrs | 2 days
54 | Develop training materials | Trainers | 120 hrs | 3 wks
55 | Conduct training usability study | Trainers | 32 hrs | 4 days
56 | Finalize training materials | Trainers | 24 hrs | 3 days
57 | Develop training delivery mechanism | Trainers | 16 hrs | 2 days
58 | Develop Help specification | Technical Communicators | 8 hrs | 1 day
59 | Develop Help system | Technical Communicators | 120 hrs | 3 wks
60 | Review Help documentation | Technical Communicators | 24 hrs | 3 days
61 | Incorporate Help documentation feedback | Technical Communicators | 16 hrs | 2 days
62 | Develop user manuals specifications | Technical Communicators | 16 hrs | 2 days
63 | Develop user manuals | Technical Communicators | 120 hrs | 3 wks
64 | Review all user documentation | Technical Communicators | 16 hrs | 2 days
65 | Incorporate user documentation feedback | Technical Communicators | 16 hrs | 2 days
66 | Identify test group | Project Manager | 8 hrs | 1 day
67 | Install/deploy software | Deployment Team | 8 hrs | 1 day
68 | Obtain user feedback | Deployment Team | 40 hrs | 1 wk
69 | Evaluate testing information | Deployment Team | 8 hrs | 1 day
70 | Determine final deployment strategy | Deployment Team | 8 hrs | 1 day
71 | Develop deployment methodology | Deployment Team | 8 hrs | 1 day
72 | Secure deployment resources | Deployment Team | 8 hrs | 1 day
73 | Train support staff | Deployment Team | 8 hrs | 1 day
74 | Deploy software | Deployment Team | 8 hrs | 1 day
75 | Document lessons learned | Project Manager | 8 hrs | 1 day
76 | Distribute to team members | Project Manager | 8 hrs | 1 day
77 | Create software maintenance team | Project Manager | 8 hrs | 1 day